## Sheet1
Defect ID | Summary | Module | Test Case ID | Severity | Priority | Status | Environment | Steps to Reproduce | Expected Result | Actual Result | Attachments | Remarks
DEF_LOGIN_01 | Password field is not masked | Login | TC_LOGIN_07 | High | High | Open | Web – Chrome (Windows 10) | 1. Open Login page 2. Enter password | Password should be masked | Password visible as plain text |  | Mock defect for learnig
DEF_REG_01 | Invalid OTP is accepted | Registration | TC_REG_11 | Critical | High | Open | Web – Chrome (Windows 10) | 1. Register with phone number 2. Enter wrong OTP | Invalid OTP error should shown | Registration completed |  | Mock defect for learnig
DEF_CART_01 | Cart total not updated correctly after qunatity change | Add to cart | TC_CART_06 | High | Medium | Open | Web – Chrome (Windows 10) | 1. Add product to cart 2. Increase quantity | Total price updated correctly | Updated price is incorrect |  | Mock defect for learnig
DEF_SESSION_01 | User session does not expire after inactivity | Non-Functional | TC_NFR_07 | High | Medium | Open | Web – Chrome (Windows 10) |  | User logged out after inactivity | User still logged in |  | Mock defect for learnig
DEF_PDP_01 | Product images are displayed incorrect | Product Details Page | TC_PDP_02 | Medium | High | Open | Web – Chrome (Windows 10) | 1. View product images Product | Product images are displayed correctly | Product images are displayed in correctly |  | Mock defect for learnig
DEF_SEARCH_01 | user cannot select product from auto-suggest dropdown | Product Search | TC_SEARCH_03 | High | High | Open | Web – Chrome (Windows 10) | 1. Click on a product from dropdown | User is redirected to the selected product’s Product Details Page | Not able select product from dropdown |  | Mock defect for learnig